## Release Plan - Winter
Summary | Issue Type | Status | Sprint | Story Points | Parent summary | Status Category
Generate syllable rules | Story | To Do | PAR Sprint 4 | 3 | Core Feature | To Do
Generate phonotactics rules | Story | To Do | PAR Sprint 4 | 8 | Core Feature | To Do
Generate vowels in a more logical way and give different values different generation chances | Task | To Do | PAR Sprint 4 | 3 | Core Fix | To Do
Move clearing vowels and consonants to store actions | Bug | To Do | PAR Sprint 4 | 1 | Core Fix | To Do
Generate All button | Task | To Do | PAR Sprint 4 | 1 | Core Feature | To Do
Host a demo website | Story | To Do | PAR Sprint 4 | 8 | Core Feature | To Do
Vertical dividers on the consonant table don't extend all the way to the bottom | Bug | To Do | PAR Sprint 4 | 1 | Core Fix | To Do
Table shouldn't resize column height when adding/removing sounds | Bug | To Do | PAR Sprint 4 | 3 | Core Fix | To Do
Vowel table shouldn't stretch to the height of the Consonant table | Bug | To Do | PAR Sprint 4 | 1 | Core Fix | To Do
Clicking on an IPA symbol while not editing shouldn't remove it | Bug | To Do | PAR Sprint 4 | 1 | Core Fix | To Do
Generate words | Story | To Do | PAR Sprint 5 | 8 | Core Feature | To Do
Words display | Story | To Do | PAR Sprint 5 | 3 | Core Feature | To Do
Generate spellings | Story | To Do | PAR Sprint 5 | 8 | Core Feature | To Do
Spelling display | Story | To Do | PAR Sprint 5 | 3 | Core Feature | To Do
Load a previously saved language | Story | To Do | PAR Sprint 6 | 5 | Account System | To Do
Save language to account | Story | To Do | PAR Sprint 6 | 5 | Account System | To Do
Logout of account | Story | To Do | PAR Sprint 6 | 3 | Account System | To Do
Login to an account | Story | To Do | PAR Sprint 6 | 3 | Account System | To Do
Register an account | Story | To Do | PAR Sprint 6 | 3 | Account System | To Do
Setup Firebase application | Story | To Do | PAR Sprint 6 | 3 | Account System | To Do